## TASKS
TASK LIST
MY TASKS | START DATE | FINISH DATE | % COMPLETE | DONE | NOTES
Glue up sheer strakes to length | 2018-02-25 | 2018-02-27 | 100% | 1 | Done over two days- one day per pair of joints due to small heated tent
Glue up bilge strakes to length | 2018-02-27 | 2018-03-01 | 100% | 1
Glue up sheer clamps to length | 2018-03-01 | 2018-03-03 | 100% | 1
Glue up bottom panels | 2018-03-02 | 2018-03-03 | 100% | 1
Glue up sheer clamps to sheer strakes | 2018-03-03 | 2018-03-04 | 100% | 1
Wire bilge strakes to bottom | 2018-03-05 | 2018-03-05 | 100% | 1
Wire sheer strakes to bilge strakes | 2018-03-05 | 2018-03-06 | 100% | 1
Install temporary beam stick | 2018-03-05 | 2018-03-05 | 100% | 1
Cut sheer clamp taper bow and stern | 2018-03-05 | 2018-03-06 | 100% | 1
Fit bulkheads into hull | 2018-03-07 | 2018-03-08 | 100% | 1
Fit fore knees into hull | 2018-03-08 | 2018-03-08 | 100% | 1
Fit aft knees into hull | 2018-03-08 | 2018-03-08 | 100% | 1
Straighten hull (winding) | 2018-03-09 | 2018-03-09 | 100% | 1
Fair the hull | 2018-03-09 | 2018-03-09 | 100% | 1
Tape off seams for filleting | 2018-03-09 | 2018-03-09 | 100% | 1
Fillet and tape bow | 2018-03-10 | 2018-03-10 | 100% | 1
2nd epoxy coat- bow | 2018-03-11 | 2018-03-11 | 100% | 1
Fillet and tape stern | 2018-03-11 | 2018-03-11 | 100% | 1
2nd epoxy coat- stern | 2018-03-12 | 2018-03-12 | 100% | 1
Fillet cockpit bulkheads | 2018-03-13 | 2018-03-13 | 100% | 1
Fillet fore and aft knees | 2018-03-13 | 2018-03-13 | 100% | 1
Fillet and tape cockpit | 2018-03-17 | 2018-03-17 | 100% | 1
2nd epoxy coat- cockpit | 2018-03-18 | 2018-03-18 | 100% | 1
Touchup epoxy coat- cockpit | 2018-03-19 | 2018-03-19 | 100% | 1
Laminate deck beam | 2018-03-08 | 2018-03-08 | 100% | 1
Install deck beam | 2018-03-22 | 2018-03-22 | 100% | 1
Scarf carlins | 2018-03-17 | 2018-03-17 | 100% | 1
Install carlins | 2018-03-22 | 2018-03-22 | 100% | 1
Prepare hull for glassing | 2018-03-23 | 2018-03-30 | 100% | 1
Glass hull and first roll of weave | 2018-03-31 | 2018-03-31 | 100% | 1
Second roll of weave | 2018-04-01 | 2018-04-01 | 100% | 1
Third roll of weave | 2018-04-02 | 2018-04-02 | 100% | 1
Optional: Fourth roll of weave if needed | 2018-04-03 | 2018-04-03 | 100% | 1
Bow end pour | 2018-06-01 | 2018-06-01 | 100% | 1
Stern end pour | 2018-06-01 | 2018-06-01 | 100% | 1
Mark and epoxy front footbrace mounts | 2018-06-02 | 2018-06-02 | 100% | 1
Mount rear footbrace riser blocks | 2018-06-02 | 2018-06-02 | 100% | 1 | Switch to Shearwater manual for deck build!
Install seat cleats (optional) |  |  |  | 0
Install deck forms | 2018-04-14 | 2018-04-14 | 100% | 1
Bevel sheer clamps | 2018-04-16 | 2018-04-16 | 100% | 1
Strip deck | 2018-04-28 | 2018-05-29 | 100% | 1
Detach and smooth underside of deck | 2018-05-30 | 2018-05-31 | 100% | 1
Fiberglass underside of deck | 2018-06-01 | 2018-06-01 | 100% | 1
Glue deck to hull | 2018-06-02 | 2018-06-02 | 100% | 1
Plane deck edges to shape | 2018-06-03 | 2018-06-03 | 100% | 1
Initial fairing of the deck to shape across grain with 80g | 2018-06-03 | 2018-06-04 | 100% | 1
Fill gaps with tinted epoxy | 2018-06-04 | 2018-06-06 | 100% | 1
Trim deck around cockpit | 2018-06-06 | 2018-06-06 | 100% | 1
Round over deck edges | 2018-06-06 | 2018-06-06 | 100% | 1
Sand deck smooth with grain using 125g | 2018-06-07 | 2018-06-07 | 100% | 1
Sand deck smooth with grain using 150g | 2018-06-07 | 2018-06-07 | 100% | 1
Sand deck smooth with grain using 220g | 2018-06-08 | 2018-06-08 | 100% | 1
Fiberglass the deck | 2018-06-08 | 2018-06-08 | 100% | 1
First roll of weave | 2018-06-09 | 2018-06-09 | 100% | 1
Second roll of weave | 2018-06-09 | 2018-06-09 | 100% | 1
Third roll of weave | 2018-06-10 | 2018-06-10 | 100% | 1
Scarf rubrails | 2018-06-09 | 2018-06-09 | 100% | 1 | Back to the Millcreek manual!
Attach rubrails | 2018-06-10 | 2018-06-11 | 100% | 1
Fit and install noseblock | 2018-06-11 | 2018-06-11 | 100% | 1
Fit and glue first coaming | 2018-06-12 | 2018-06-12 | 100% | 1
Fit and glue second coaming | 2018-06-13 | 2018-06-13 | 100% | 1
Fit and install back coaming | 2018-06-13 | 2018-06-13 | 100% | 1
Fit and install port coaming rim | 2018-06-14 | 2018-06-14 | 100% | 1
Fit and install starboard coaming rim | 2018-06-15 | 2018-06-15 | 100% | 1
Fit and install back coaming rim | 2018-06-15 | 2018-06-15 | 100% | 1
Sand, stain and seal coamings | 2018-06-16 | 2018-06-16 | 100% | 1
Drill bow and stern holes for handles | 2018-07-06 | 2018-07-06 | 100% | 1
Sand glass and fill as needed | 2018-06-17 | 2018-07-14 | 100% | 1
Create rear hatch opening, cover | 2018-07-04 | 2018-07-04 | 100% | 1
Glue rear hatch seal spacers | 2018-07-04 | 2018-07-04 | 100% | 1
Glue, sand seal rear hatch seal sill | 2018-07-05 | 2018-07-06 | 100% | 1
Create front hatch opening, cover | 2018-07-03 | 2018-07-03 | 100% | 1
Glue front hatch seal spacers | 2018-07-03 | 2018-07-03 | 100% | 1
Glue, sand, seal front hatch seal sill | 2018-07-04 | 2018-07-06 | 100% | 1
Sand and seal front hatch cover | 2018-07-05 | 2018-07-14 | 100% | 1
Sand and seal rear hatch cover | 2018-07-07 | 2018-07-14 | 100% | 1
Drill, fill, drill front hatch loop holes | 2018-07-06 | 2018-07-13 | 100% | 1
Drill, fill, drill rear hatch loop holes | 2018-07-06 | 2018-07-13 | 100% | 1
Create four hatch hooks | 2018-07-14 | 2018-07-14 | 100% | 1
Glue front hatch hooks | 2018-07-16 | 2018-07-16 | 100% | 1
Fiberglass front hatch hooks |  |  |  | 0
Glue rear hatch hooks | 2018-07-16 | 2018-07-16 | 100% | 1
Fiberglass rear hatch hooks |  |  |  | 0
Sand hooks and anchors as needed | 2018-07-14 | 2018-07-14 |  | 0
Varnish hull 1st coat | 2018-07-14 | 2018-07-14 | 100% | 1
Varnish hull 2nd coat | 2018-07-15 | 2018-07-15 | 100% | 1
Varnish hull 3rd coat | 2018-07-16 | 2018-07-16 | 100% | 1
Varnish hull, 4th coat |  |  |  | 0
Varnish deck, 5th coat |  |  |  | 0
Varnish deck, hatch covers 1st coat | 2018-07-17 | 2018-07-17 | 100% | 1
Varnish deck, hatch covers 2nd coat | 2018-07-18 | 2018-07-18 | 100% | 1
Varnish deck, hatch covers 3rd coat | 2018-07-19 | 2018-07-19 | 100% | 1
Varnish deck, hatch covers 4th coat |  |  |  | 0
Varnish hull, hatch covers 5th coat |  |  |  | 0
Make slat seats | 2018-07-04 | 2018-07-05 | 100% | 1
Apply finish to slat seats | 2018-07-16 | 2018-07-19 | 100% | 1
Install slat seats | 2018-07-19 | 2018-07-21 | 100% | 1
Create eight wood bungee anchors | 2018-07-19 | 2018-07-19 | 100% | 1
Glue four bungee anchors in front hatch | 2018-07-21 | 2018-07-21 | 100% | 1
Glue four bungee anchors in rear hatch | 2018-07-21 | 2018-07-21 | 100% | 1
Fiberglass front bungee anchors |  |  |  | 0
Fiberglass rear bungee anchors |  |  |  | 0
Install hatch weatherstripping, covers | 2018-07-21 | 2018-07-21 | 100% | 1
Install hatch bungees- front | 2018-07-21 | 2018-07-21 | 100% | 1
Install bungees - rear | 2018-07-21 | 2018-07-21 | 100% | 1
Finish installing foot braces | 2018-07-21 | 2018-07-21 | 100% | 1
Add handles | 2018-07-17 | 2018-07-17 | 100% | 1